AWS FIRST CLOUD AI JOURNEY – PROJECT PLAN

Devteria Team – First Cloud Journey – Devteria Game Store Platform

December 8, 2025

# TABLE OF CONTENTS

| 1 BACKGROUND AND MOTIVATION | 3 |
| --- | --- |
| 1.1 EXECUTIVE SUMMARY | 3 |
| 1.2 PROJECT SUCCESS CRITERIA | 4 |
| 1.3 ASSUMPTIONS | 4 |
| 2 SOLUTION ARCHITECTURE / ARCHITECTURAL DIAGRAM | 5 |
| 2.1 TECHNICAL ARCHITECTURE DIAGRAM | 5 |
| 2.2 TECHNICAL PLAN | 6 |
| 2.3 PROJECT PLAN | 7 |
| 2.4 SECURITY CONSIDERATIONS | 8 |
| 3 ACTIVITIES AND DELIVERABLES | 9 |
| 3.1 ACTIVITIES AND DELIVERABLES | 9 |
| 3.2 OUT OF SCOPE | 10 |
| 3.3 PATH TO PRODUCTION | 10 |
| 4 EXPECTED AWS COST BREAKDOWN BY SERVICES | 11 |
| 5 TEAM | 12 |
| 6 RESOURCES & COST ESTIMATES | 13 |
| 7 ACCEPTANCE | 14 |

# 1  BACKGROUND AND MOTIVATION

## 1.1  EXECUTIVE SUMMARY

Devteria Game Store is a scalable cloud-based e-commerce platform for digital game licensing and distribution. Built entirely on AWS infrastructure, it delivers secure user authentication, real-time inventory management, automated order processing, and global content delivery.

The platform addresses critical challenges faced by traditional digital stores:

Traffic spike handling during sales events

Complex authentication processes reducing conversions

Manual inventory management causing overselling

Lack of real-time analytics and insights

High infrastructure costs for peak capacity planning

Devteria leverages AWS services including:

CloudFront + S3 for fast global content delivery

Cognito for secure authentication with MFA

API Gateway + Lambda for serverless backend logic

RDS PostgreSQL + S3 for reliable data storage

SQS + SNS for asynchronous order processing

CodePipeline for continuous deployment

The solution supports thousands of concurrent users with 99.9% uptime guarantee and achieves cost efficiency through serverless architecture that scales automatically based on demand.

## 1.2  PROJECT SUCCESS CRITERIA

Achieve page load time of less than 2 seconds globally through CloudFront CDN

Maintain 99.9% system uptime using AWS managed services and Multi-AZ deployment

Handle 10x traffic spikes automatically through Lambda auto-scaling and EC2 Auto Scaling Groups

Ensure zero security breaches with Cognito MFA, IAM policies, and encryption at rest/transit

Complete CI/CD pipeline enabling deployments in less than 10 minutes via CodePipeline

Reduce cart abandonment by 40% through simplified Cognito authentication flow

Decrease infrastructure management time by 60% using serverless components

Maintain stable performance for 10,000 monthly active users with room to scale to 100K+

Ensure database consistency with RDS automated backups and point-in-time recovery (7-day retention)

Achieve PCI-ready security posture for payment processing integration

## 1.3  ASSUMPTIONS

The customer will provide accurate business requirements and game licensing workflows

GitLab repository and credentials will be accessible for CI/CD integration

All workloads will operate within one AWS Region (us-east-1 or ap-southeast-1)

No on-premise system integration required during the initial phase

Frontend code (React/Next.js) supports static hosting via S3 + CloudFront

The project will not include Machine Learning or AI recommendation modules in Phase 1

Traffic is expected to remain within reasonable limits (10,000 users initially)

Payment gateway integration will use third-party APIs (Stripe/PayPal) via Lambda

Game files will be uploaded manually or via admin dashboard to S3

Customer accepts AWS Free Tier limitations and cost estimates provided

# 2  SOLUTION ARCHITECTURE / ARCHITECTURAL DIAGRAM

## 2.1  TECHNICAL ARCHITECTURE DIAGRAM

[Architecture Diagram - See technical documentation for visual representation]

The Devteria Game Store architecture consists of the following layers:

1. Edge Networking Layer

Route 53: DNS management and domain hosting

CloudFront: Global CDN for caching static assets and reducing latency (<2s page load)

AWS Shield: DDoS protection (Standard tier included)

2. Application Layer

Frontend: React/Next.js app hosted on S3 + CloudFront

API Gateway: RESTful API entry point with request validation and throttling

Lambda Functions: Serverless backend logic (authentication, catalog browsing, order processing)

EC2 Auto Scaling Group: Microservices for complex business logic (2x t3.medium instances)

Application Load Balancer: Distributes traffic to EC2 instances

3. Data Layer

RDS PostgreSQL Multi-AZ: User accounts, game catalog, orders, license keys

S3 Buckets: Game installation files, promotional assets, static website hosting

SQS: Message queue for asynchronous order processing and license generation

SNS: Email notifications for order confirmations and promotions

4. Networking Layer

VPC: Isolated network environment (10.0.0.0/16)

Public Subnets: ALB, NAT Gateway for internet access

Private Subnets: EC2 instances, RDS database (no direct internet exposure)

Internet Gateway: External access for public-facing resources

5. CI/CD Layer

GitLab: Source code repository with version control

CodePipeline: Orchestrates automated build and deployment workflow

CodeBuild: Compiles code, runs tests, creates deployment artifacts

EC2 Deployment: Automated deployment to instances via CodeDeploy

6. Security & Monitoring Layer

Cognito: User authentication and authorization with MFA support

IAM: Fine-grained access control with least privilege policies

Secrets Manager: Secure storage for database credentials with automatic rotation

CloudWatch: Metrics collection, logs aggregation, and alarms

CloudTrail: API audit logging for compliance

User Flow:

User accesses site → Login via Cognito → Browse games (API Gateway → Lambda → RDS) → Add to cart → Checkout → Payment processing → License generation (SQS) → Email notification (SNS) → Secure download from S3

Architecture diagram reference: /images/2-Proposal/proposal.jpg

## 2.2  TECHNICAL PLAN

The partner will implement the architecture using Infrastructure as Code (IaC) via AWS CloudFormation to ensure consistent, reproducible, and version-controlled deployments.

CI/CD Pipeline Stages:

Source: GitLab webhook triggers CodePipeline on commit

Build: CodeBuild compiles React frontend and Node.js backend

Test: Automated unit tests, integration tests, and security scans

Deploy: Frontend to S3, Backend to EC2 via CodeDeploy with blue/green deployment

Additional Technical Configurations:

IAM roles restricted following least-privilege model (separate roles for Lambda, EC2, RDS access)

RDS automated backups with 7-day retention and point-in-time recovery

CloudWatch alarms for CPU >80%, memory >85%, database connections >80%, API 5xx errors

S3 versioning enabled for rollback capability

Cognito user pool with strong password policies (min 8 chars, uppercase, lowercase, numbers, symbols)

Lambda provisioned concurrency to eliminate cold starts during peak hours

## 2.3  PROJECT PLAN

The project follows an Agile Scrum framework across 6 months (24 weeks), organized into 12 sprints of 2 weeks each.

Team Structure:

Project Manager: Overall coordination, stakeholder communication, risk management

Cloud Solutions Architect: Design AWS infrastructure, create IaC templates, technical leadership

Backend Developers (2): Build Lambda functions, EC2 microservices, API Gateway integration

Frontend Developer: Develop React/Next.js application, Cognito integration

DevOps Engineer: Set up CI/CD pipeline, monitoring, infrastructure automation

QA Engineer: Functional testing, performance testing, security testing

Communication Cadence:

Daily standup: 15-minute team sync (blockers, progress, plans)

Weekly sprint planning: Review backlog, assign tasks, estimate effort

Bi-weekly sprint review: Demo completed features to stakeholders

Bi-weekly retrospective: Team improvement discussions

Monthly technical report: Progress update, metrics, risks to customer

Slack/Teams: Real-time collaboration and quick questions

## 2.4  SECURITY CONSIDERATIONS

Access Control:

Cognito user pool with email verification and optional MFA (TOTP-based)

IAM roles with least privilege principle

API Gateway request validation, throttling (1000 req/sec), and API keys for partners

Infrastructure Security:

EC2 instances in private subnets (no direct internet access)

Security Groups with minimal required ports (ALB: 443/80, EC2: 8080, RDS: 5432)

CloudFront with HTTPS-only, AWS Shield Standard for DDoS protection

Data Protection:

RDS encryption at rest using AWS KMS (AES-256)

S3 bucket encryption (SSE-S3) and versioning enabled

SSL/TLS for all data in transit (ACM-issued certificates)

Secrets Manager for database credentials with automatic 30-day rotation

Detection & Response:

CloudTrail for API audit logging (all actions tracked, 90-day retention)

CloudWatch alarms for failed login attempts, unusual traffic patterns, high CPU/memory

SNS notifications for critical security events

Regular security audits (quarterly) and penetration testing (before launch)

Incident Management:

Automated backup and restore procedures documented in runbooks

RDS automated backups with 7-day retention and point-in-time recovery

Disaster recovery plan: RTO < 4 hours, RPO < 1 hour

Incident response runbook for common scenarios (DB failover, DDoS, data breach)

# 3  ACTIVITIES AND DELIVERABLES

## 3.1  ACTIVITIES AND DELIVERABLES

| Phase | Timeline | Activities | Deliverables | Man-days |
| --- | --- | --- | --- | --- |
| Assessment | Week 1-2 | Requirements gathering, architecture design, ERD modeling, cost estimation | Architecture document, project plan, ERD diagrams | 10 |
| Infrastructure | Week 3-6 | VPC, subnets, IGW, NAT, RDS, S3, Cognito setup | AWS environment ready, networking configured | 15 |
| Backend Dev | Week 7-12 | Lambda APIs, EC2 microservices, API Gateway integration | Working APIs for auth, catalog, orders | 25 |
| Frontend Dev | Week 11-14 | React app, Cognito integration, S3 + CloudFront deployment | User-facing web application | 18 |
| Integration | Week 15-18 | Payment gateway, admin dashboard, CI/CD setup | End-to-end workflow functional | 20 |
| Testing | Week 19-22 | Load testing, security audits, UAT, bug fixes | Test reports, security audit | 15 |
| Launch | Week 23-24 | Beta release, monitoring, production deployment, handover | Production system, documentation | 7 |

## 3.2  OUT OF SCOPE

The following items are excluded from the initial project scope:

AI/ML recommendation engine for personalized game suggestions

Mobile application development (iOS/Android native apps)

Integration with external inventory management or ERP systems

Multi-region failover and disaster recovery setup

Advanced analytics and business intelligence dashboards

Social media login integration (Google, Facebook)

Live chat customer support system

Advanced fraud detection beyond basic payment gateway features

Game streaming or cloud gaming capabilities

Marketplace features (user-to-user game trading)

## 3.3  PATH TO PRODUCTION

The initial release (Phase 1 / MVP) includes core functionalities:

User registration and authentication via Cognito

Game catalog browsing with search and filtering

Shopping cart and checkout workflow

Payment processing via Stripe/PayPal integration

Automated license key generation and delivery

Secure game file downloads from S3

Admin dashboard for inventory management

Basic reporting and analytics

To achieve production-ready status, the following enhancements are planned:

Enhanced error handling and user-friendly error messages

API rate limiting and request throttling via API Gateway

Database query optimization and indexing

Comprehensive audit trail dashboards in CloudWatch

Penetration testing by third-party security firm

Load testing to validate 10x traffic spike handling

Customer acceptance testing (UAT) with beta users

# 4  EXPECTED AWS COST BREAKDOWN BY SERVICES

Estimated monthly cost for 10,000 users and 1,000 orders/month: ~$228

| AWS Service | Monthly Cost (USD) |
| --- | --- |
| CloudFront (10M requests, 50GB transfer) | $8 |
| S3 (100GB storage + requests) | $3 |
| API Gateway (1M requests) | $3.50 |
| Lambda (5M invocations, 512MB) | $17.50 |
| EC2 (2x t3.medium instances) | $60 |
| RDS PostgreSQL (db.t3.small Multi-AZ) | $50 |
| Application Load Balancer | $22 |
| Cognito (10K users) | $28 |
| SQS + SNS + CloudWatch + Other | $36 |

Total Monthly Cost: ~$228

Estimated Annual Cost: ~$2,736

Scaling Projections:

• 50,000 users: ~$650/month

• 100,000 users: ~$1,200/month

Assumptions:

Traffic under 10,000 users/month initially

AWS Free Tier credits applied where eligible

Data transfer within same AWS region

# 5  TEAM

Partner Executive Sponsor

| Name | Title | Description | Email / Contact Info |
| --- | --- | --- | --- |
| Nguyen Van A | Director of Cloud Services | Overall project accountability and strategic direction | nguyenvana@devteria.com |

Project Stakeholders

| Name | Title | Stakeholder for | Email / Contact Info |
| --- | --- | --- | --- |
| Tran Thi B | Product Manager | Business requirements, UX decisions | tranthib@devteria.com |
| Le Van C | Senior QA Engineer | Testing and quality assurance | levanc@devteria.com |
| Pham Thi D | IT Operations Manager | Infrastructure and deployment | phamthid@devteria.com |

Partner Project Team

| Name | Title | Role | Email / Contact Info |
| --- | --- | --- | --- |
| Hoang Van E | Project Manager | Project coordination | hoangvane@partner.com |
| Nguyen Thi F | Cloud Solutions Architect | Architecture design, technical lead | nguyenthif@partner.com |
| Tran Van G | Senior Backend Developer | Lambda and EC2 development | tranvang@partner.com |
| Pham Thi H | Frontend Developer | React application development | phamthih@partner.com |
| Le Van I | DevOps Engineer | CI/CD and infrastructure automation | levani@partner.com |
| Nguyen Van J | QA Engineer | Testing and quality assurance | nguyenvanj@partner.com |

# 6  RESOURCES & COST ESTIMATES

Resource Rates:

| Resource | Rate (USD) / Hour |
| --- | --- |
| Solution Architects (1 headcount) | $80 |
| Engineers (4 headcount) | $60 |
| QA Engineer (1 headcount) | $55 |

Project Phase Hours Breakdown:

| Project Phase | Solution Architects | Engineers | QA Engineer | Total Hours |
| --- | --- | --- | --- | --- |
| Assessment | 80 | 0 | 0 | 80 |
| Infrastructure | 120 | 0 | 0 | 120 |
| Backend Dev | 40 | 200 | 0 | 240 |
| Frontend Dev | 0 | 144 | 0 | 144 |
| Integration | 40 | 160 | 0 | 200 |
| Testing | 20 | 0 | 120 | 140 |
| Launch | 16 | 40 | 0 | 56 |
| Total Hours | 316 | 544 | 120 | 980 |

Total Cost Calculation:

• Solution Architects: 316 hours × $80/hour = $25,280

• Engineers: 544 hours × $60/hour = $32,640

• QA Engineer: 120 hours × $55/hour = $6,600

Total Project Cost: $64,520

Cost Contribution Distribution:

| Party | Contribution (USD) | % of Total |
| --- | --- | --- |
| Customer | $32,260 | 50% |
| Partner | $25,808 | 40% |
| AWS | $6,452 | 10% |

# 7  ACCEPTANCE

Upon completion of each deliverable listed in Section 3.1, the partner will submit deliverables along with a formal Acceptance Form for customer review.

Acceptance Process:

Partner completes deliverable and internal quality checks

Partner submits deliverable with Acceptance Form to customer

Customer has 8 business days from submission date to review

Customer Review Options:

Approve: Deliverable meets acceptance criteria, project proceeds to next phase

Reject: Deliverable does not meet criteria, partner receives detailed feedback specifying required changes

Rejection Handling:

Partner corrects deliverable according to feedback

Partner resubmits for another review cycle (another 8 business days)

Process repeats until approval or escalation

Auto-Acceptance:

If customer does not respond within 8-business-day acceptance period, deliverable is automatically accepted and project proceeds to next phase.

Documentation:

All acceptances (explicit or auto) will be documented and signed by both parties

Maintains clear audit trail of project progress and completion milestones

Signatures required from Customer Executive Sponsor and Partner Project Manager